Guinea GCF Readiness — Response Package to Junghwan

Revised budget workbook · Section 5 GPP output-level mapping · Comment-by-comment response matrix

Prepared by Alpha Oumar KALOGA — GreenTransformation2050 (GT2050) · 2026-07-21

A.  Reply email to Junghwan

To: Junghwan (GCF)   |   From: Alpha KALOGA, GT2050

Subject: Guinea GCF Readiness — revised budget workbook (30/60/10 rebalanced, USD 350/day local rate, PMC compliant)

Dear Junghwan,

Thank you for your careful review and the corrected workbook. Please find attached the revised Readiness budget package, which addresses your comments in full.

In summary: the deliverable budget has been rebalanced to the 30% / 60% / 10% split across Objectives 1, 2 and 3; every local consultant line is now set at the USD 350/day benchmark (international consultants remain at USD 500/day, per your comment); and project management cost has been brought to 7.43%, within the 7.5% Readiness threshold. The D8 Country Programme deliverable is retained blank so that the Objective 2 total formula stays intact, consistent with your note. D9 (five firm-developed Concept Notes, USD 228,000) and D10 (three fully-developed Funding Proposals, USD 700,000) are preserved, and the Disbursement Schedule and Fee Request now tie out exactly to the Budget Plan. Milestones have been added for every deliverable, and the Budget Notes — including the two previously in French — have been translated and updated to reflect these changes. The implementation and disbursement schedules have also been reconciled to the confirmed 36-month period; all milestones, evaluation and closure actions now fall within Years 1-3.

The revised total request is USD 2,620,590, which reduces the overage above the indicative USD 2,500,000 ceiling to USD 120,590. The NDA validates this revised total for submission.

On the Logical Framework, Section 5 (output level) has been reconciled across the proposal and both logframes and validated by the NDA for GPP entry.

We remain at your disposal for any further comments or adjustments.

With kind regards,

Alpha Oumar KALOGA

President, GreenTransformation2050 (GT2050)

greentransformation2050@gmail.com · a.kaloga@gt2050.org

B.  Section 5 — Logical Framework (output level): GPP field-mapping

Ready-to-enter values for the GPP structured/drop-down fields. The canonical values below are reconciled with the proposal and both logframes and are validated for entry.

| GPP field | Value to select / enter |
| --- | --- |
| Objective 1 (dropdown) | Capacity-building for climate-finance coordination and setting up the enabling environment for integrated climate investment |
| Outcome 1.1 (tick ☒) | NDAs/focal points have enhanced capacity to fulfil roles, responsibilities and policy requirements, incl. coordination mechanisms |
| Output 1.1.1 | NDA/focal point and other climate stakeholders have enhanced capacity to develop, advance and implement NDCs, NAPs and LTSs |
| Indicator | Proportion of NDA/focal point, Coordination Mechanism and other stakeholders reporting enhanced capacity (Individuals: X/total) |
| Unit | Percentage; denominator = 120 participants |
| Baseline / Target | 0% / ≥70% of 120 participants reporting enhanced capacity |
| Disaggregation | Sex; stakeholder group; strategic framework (NDC/NAP/LTS) |
| Deliverables (tick) | ☒ D1 · ☒ D2 |
| Output 1.1.2 | An inclusive Coordination Mechanism has enhanced capacity to fulfil its mandate |
| Indicator 1 / Unit | An inclusive Coordination Mechanism or Country Platform is supported · No. of Coordination Mechanisms / Country Platforms |
| Baseline / Target | 0 / 1 (National Climate Finance Coordination Platform) |
| Indicator 2 / Unit | Number of coordination meetings or dialogues undertaken · No. of Meetings/Dialogues |
| Baseline / Target | 0 / 9 meetings or dialogues during Months 1-36 |
| Deliverables (tick) | ☒ D2 |
| Outcome 1.2 (tick ☒) | Developing countries design and implement strategic frameworks (NDC/NAP/LTS), policies and instruments |
| Output 1.2.1 | Inclusive strategic frameworks (NDCs, NAPs, LTSs) and policy instruments created, updated and/or strengthened |
| Indicator / Unit | Number of strategic frameworks and policy instruments created/updated/strengthened · No. of frameworks/instruments |
| Baseline / Target | 0 / 3 strategic frameworks advanced (NAP, NDC, LTS) + ≥1 private-sector policy instrument |
| Disaggregation | Type of instrument (NDC, NAP, LTS, policy/regulation) |
| Deliverables (tick) | ☒ D3 · ☒ D4 · ☒ D5 · ☒ D6 |
| Outcome 1.3 (tick ☒) | DAEs have met/maintained GCF accreditation standards and strengthened programming capacities |
| Output 1.3.1 | Institutional gaps of direct access applicants and DAEs addressed to obtain and/or maintain accreditation |
| Indicator / Unit | Number of direct access entities supported to meet accreditation requirements · No. of Entities |
| Baseline / Target | 0 / 2 (ANAFIC, Access Bank Guinea — subject to GCF Accreditation Team confirmation) |
| Deliverables (tick) | ☒ D7 |
| Objective 2 (dropdown) | Paradigm-shifting GCF pipeline development and implementation for adaptation and mitigation, guided by USP-2 programming targets |
| Outcome 2.1 (tick ☒) | Developing countries have developed/updated country programmes — retained in architecture |
| Output 2.1.1 / D8 | Country Programme Document — NOT APPLICABLE / REMOVED (per GCF comment 2.1.1); function absorbed into Outputs 1.1.2 & 1.2.1. Baseline/Target N/A. D8 unticked (☐), no budget. |
| Outcome 2.2 (tick ☒) | Developing countries have developed high-quality concept notes linked to approved GCF proposals |
| Output 2.2.1 | NDA, DAEs and stakeholders have enhanced capacity on Concept Note and/or Funding Proposal development |
| Indicator / Unit | Primary: number of studies, assessments and actions supporting investment-grade CNs/FPs; supplemental: project-preparation participants and percentage reporting enhanced capacity · No. of studies/actions; participants; percentage |
| Baseline / Target | 0 / ≥5 studies or assessments; 60 participants; ≥70% reporting enhanced capacity |
| Output 2.2.2 | Investment-grade Concept Notes and submission-ready Funding Proposals aligned with national priorities; GCF screening status reported separately |
| Indicator / Unit | Number of investment-grade CNs prepared and NDA-validated; number of submission-ready FPs prepared and NDA-validated · No. of CNs / No. of FPs |
| Baseline / Target | 0 / 5 Concept Notes and 3 Funding Proposals |
| Deliverables (tick) | ☒ D9 (5 CNs) · ☒ D10 (3 FPs) |
| Outcome 2.3 (tick ☒) | NDAs and DAEs have enhanced processes and systems to oversee implementation, financial management, monitoring and reporting |
| Output 2.3.1 | NDA and DAEs have enhanced capacity, processes and systems to design, oversee and implement climate programmes/projects |
| Indicator / Unit | Primary: number of institutions reporting enhanced processes and systems; supplemental: number of systems/process packages established or strengthened · No. of institutions; no. of systems/process packages |
| Baseline / Target | 0 / 3 institutions reporting enhanced capacity + 3 systems/process packages |
| Deliverables (tick) | ☒ D11 |
| Objective 3 (dropdown) | Knowledge-sharing and learning to enhance national and regional cooperation on climate programming and financing |
| Outcome 3.1 (tick ☒) | Developing countries have made use of knowledge products to address policy gaps |
| Output 3.1.1 | Climate knowledge products and resources are generated and disseminated |
| Indicator / Unit | Number of knowledge products produced and disseminated · No. of Knowledge Products |
| Baseline / Target | 0 / ≥5 knowledge products or resources |
| Deliverables (tick) | ☒ D12 · ☒ D13 |
| Outcome 3.2 (tick ☒) | Enhanced collaboration among developing countries — transboundary/regional/South-South cooperation |
| Output 3.2.1 | Regional or South-South partnerships, programmes, policies, MOUs and/or collaboration mechanisms established |
| Indicator / Unit | Number of regional/South-South partnerships or mechanisms established · No. of Partnerships |
| Baseline / Target | 0 / 2 (Morocco, Senegal) |
| Deliverables (tick) | ☒ D14 |

C.  Comment-by-comment response matrix

| Tab | His instruction | What was changed | Assumption / flag |
| --- | --- | --- | --- |
| Impl. Plan | Apply distinct colour-coding to activities, deliverables and milestones so each category is visually separable. | Legend colour-coded (Activity = blue, Deliverable = green, Milestone = amber). All markers are aligned to the confirmed 36-month period; Year 4 is marked not applicable. | Timeline and disbursement phasing aligned to Years 1-3. |
| Budget Plan | Add the missing milestones so each deliverable’s budget is justified against a milestone. | Named milestones added for D1–D14 in the Milestones column (e.g. M2.1 Platform established; M10.2 three FPs prepared). D8 left without a milestone (removed). | Milestone titles derived from the Implementation-Plan activities. |
| Budget Plan | Set the local consultant rate to USD 350/day in every deliverable. | All ‘Consultant – Individual – Local’ deliverable lines set to USD 350/day (was 400 in several lines). Verified: 0 local lines off-350. | PMC coordinator is a monthly rate (USD 4,000/mo), distinct from the 350/day deliverable rate. |
| Budget Plan | Rebalance so the total per objective is Obj1 30% / Obj2 60% / Obj3 10%. | Deliverable budgets set to USD 660,000 / 1,320,000 / 220,000 = exactly 30/60/10. Obj1 trimmed (esp. D1, D7 — GIN-RS-003 duplication), Obj2 strengthened via D11, Obj3 lightly trimmed. | Quantities/lump sums adjusted to land on shares; D9/D10 kept at agreed amounts. |
| Budget Plan | Enforce PMC ≤ 7.5% of the total. | PMC set to USD 168,000 = 7.43% of the deliverables + evaluation base (audit 15,000; coordinator 144,000; FM/reporting 9,000). Max-PMC cell updated from 5% to the 7.5% threshold. | — |
| Budget Plan | Leave row D8 blank; do not delete it; restore column L if broken. | D8 rows kept with blank budget cells; milestone cell cleared; Note G reference added. Column L intact (L36 = SUM(J36:J51)); Objective 2 total unaffected. | — |
| Budget Category | Add categories if the existing set is insufficient; reference consistently. | Existing 10 categories cover every line; none added. All lines use exact category strings; the SUMIF category summary ties to USD 2,200,000. | Existing categories sufficient. |
| Disbursement | Under each D1, D2… insert the specific deliverable name and its % of the work; do not alter the cumulative column. | Each active deliverable and milestone carries its title, percentage and phased amount. All Year 4 amounts were moved into Year 3; the cumulative formulas remain intact and reconcile to USD 2,620,590. | Confirmed 36-month implementation period. |
| Fee request | Realign every number to the revised Budget Plan so the two tie out exactly. | Fee-request lines rescaled to total USD 124,790 = 5% of sub-total; fee-percentage cell resolves to exactly 5.0%. | Lines rescaled proportionally; residual trued up on the closure line. |
| Budget Notes | Translate Notes B and D from French to English and update their content. | Notes B (local consultants) and D (workshops/events) translated to English and updated to 350/day, revised workshop counts and the new PMC. Figures in A, C, H, I, J, K, L refreshed; rebalancing Note M added. | Non-required notes updated too, to avoid stale figures. |
| Section 5 | Produce ready-to-enter GPP output-level values. | Canonical GPP values reconciled across the proposal and both logframes. Primary RRMF indicators and supplemental programme indicators are clearly distinguished; all 'confirm' flags were resolved. | Validated canonical mapping for GPP entry. |
| Budget (8.1) | Maintain international consultant rate at USD 500/day (GCF comment #5). | All international consultant lines set at USD 500/day. Verified: 0 international lines off-500. | — |
| Budget (8.1) | Reflect agreed scope: D9 = 228,000 (5 CNs), D10 = 700,000 (3 FPs), D8 removed, evaluation reconciled. | D9 = 228,000 and D10 = 700,000 preserved with clean unit labels and 350/day local lines; D8 removed; evaluation corrected from residual USD 10,000 to reconciled USD 60,000. | Evaluation corrected to 60,000 (memo & Note K) — flagged as a data-fix. |
| Whole workbook | Grand total may change; correctness of lines takes priority — state the new total. | New total = USD 2,620,590. The NDA validates the revised total for submission. | NDA validation confirmed. |

D.  Verification results (all checks passed)

1. Objective shares = 30.00% / 60.00% / 10.00%, sum 100%.  ✔

2. PMC = 7.43% ≤ 7.5%.  ✔

3. Budget Plan, Disbursement and Fee Request tie out (fee = 5.0%; disbursement grand = USD 2,620,590).  ✔

4. D8 blank and retained; column L formulas intact.  ✔

5. Every local consultant rate = USD 350/day (international = USD 500/day).  ✔

6. All 14 GCF comments addressed and documented. ✓
7. All implementation, evaluation and closure actions fall within Months 1-36; Year 4 is not applicable. ✓
8. Proposal, logframes and GPP mapping use one canonical indicator set; NDA validation is stated. ✓