CALL FOR

PROPOSALS

Strengthening Guinea’s national system for assessing, governing and financing responses to climate-induced loss and damage

CFP reference number: CFP/SN/24039/2026/GUI/028

# BACKGROUND

## The Santiago Network

The Santiago Network was established under the Warsaw International Mechanism for loss and damage (WIM) in 2019 as a mechanism to catalyse technical assistance (by relevant organizations, bodies, networks, and experts, or OBNEs), to avert, minimize and address loss and damage associated with the adverse effects of climate change at the local, national, and regional level. The technical assistance is for developing countries that are particularly vulnerable to the adverse effects of climate change. To streamline the process, terms of reference for the Santiago Network were adopted in 2022, including establishing its hosted secretariat to coordinate its functions, an Advisory Board to provide oversight and guidance, and a network of members to provide technical assistance. The United Nations Office for Disaster Risk Reduction (UNDRR) and the United Nations Office for Project Services (UNOPS) were selected as the hosts of the Santiago Network Secretariat in 2023. The Santiago Network Secretariat administers, through UNOPS, the funds provided to the Santiago Network to support technical assistance, in accordance with the respective regulations and rules of UNOPS.

Technical assistance through the network will be provided in a demand-driven manner and developed through an inclusive and country-led process, taking into account the needs of vulnerable people, Indigenous Peoples and local communities.

The Santiago Network is further guided by six functions.

- Effective implementation of the functions of the WIM;

- Catalysing demand-driven technical assistance, including by identifying, prioritizing, and communicating technical assistance needs and priorities;

- Facilitating and catalysing collaboration, coordination, coherence and synergies among OBNEs to deliver technical assistance effectively and efficiently;

- Facilitating the consideration of a wide range of topics;

- Facilitating the development and sharing of knowledge and information on loss and damage; and

- Facilitating access to finance, capacity building and technology through technical assistance.

## Catalysing technical assistance through the Santiago Network

The scope of technical assistance includes a wide range of topics relevant to averting, minimizing and addressing loss and damage associated with climate change. Requests for technical assistance are further guided by the Guidelines and procedures for responding to requests for technical assistance that articulate the criteria governing requests for technical assistance, and the process for making and responding to requests, as well as provide the template for developing countries to submit requests. OBNEs designated as members of the Santiago Network will be able to respond to these requests in keeping with the established open and transparent process.* The provision of technical assistance must also be aligned with the Guidelines on preventing potential and addressing actual and perceived conflicts of interest in relation to the Santiago network.

*Note: For the purposes of this Call for Proposals, interested OBNEs that submit their Expression of Interest to become a member of the Santiago Network prior to the submission deadline indicated in this Call for Proposals and are subsequently admitted as members in line with the membership guidelines will be considered (see also preliminary screening criteria outlined in section 4).

# PARTICULARS OF THE REQUEST FOR TECHNICAL ASSISTANCE

## Title of the technical assistance request

Strengthening Guinea’s national system for assessing, governing and financing responses to climate-induced loss and damage.

## Country and policy context

The Republic of Guinea is increasingly vulnerable to the adverse effects of climate change, facing both sudden-onset events, such as floods and landslides, and slow-onset processes, including drought, sea level rise, and environmental degradation. The frequency, severity and duration of these hazards are intensifying due to increasingly erratic rainfall, and rising temperatures, together with poor land-use planning, pollution, and limited access to essential water, sanitation, and health infrastructure. According to the Stratégie Nationale de Réduction des Risques de Catastrophes (SNRRC) 2024–2030 and the World Bank Contingent Emergency Response Project (CERP), such risks are further aggravated by socio-economic fragility, urban expansion, and inadequate service delivery, particularly in densely populated areas like Conakry.

Between 1980 and 2020, floods and epidemics alone accounted for over 80% of disaster-related human impacts in Guinea. Nearly two-thirds of households report experiencing shocks—ranging from harvest and livestock losses to income reductions and food insecurity. Vulnerable populations, including women, children, and the extreme poor, are disproportionately affected. While the country has mobilized climate finance averaging USD 200 million annually (2016–2020), the resilience financing gap is estimated at USD 1.39 billion per year through 2030.

Slow-onset climate processes represent an equally critical but systematically underestimated driver of Guinea’s climate-induced loss and damage. Prolonged droughts in Upper and Middle Guinea are reducing agricultural productivity, depleting water sources, and forcing seasonal and permanent migration from rural areas. Sea-level rise and coastal erosion along Guinea’s 300 km coastline are degrading mangrove ecosystems, saltwater-intruding into rice-growing systems, and destroying dikes and infrastructure in coastal prefectures including Boffa, Boké, and Forécariah. Salinisation is rendering formerly productive farmland permanently unviable for staple crop production. These slow-onset processes disproportionately affect women, who constitute the majority of subsistence farmers, mangrove harvesters, and aquaculture producers in coastal and rural zones. Losses to traditional livelihoods, land tenure, cultural practices, and ecosystem services associated with mangrove systems constitute significant non-economic losses and damages that are currently unmeasured and unreported in Guinea’s national systems.

Guinea’s institutional architecture for loss and damage management is fragmented, under-resourced, and lacking a standardised methodology. The Stratégie Nationale de Réduction des Risques de Catastrophes (SNRRC 2024–2030), led by Centre National de Gestion des Catastrophes et des Urgences Environnementales (CENAGCUE), which is responsible for national coordination on disaster risk reduction, establishes a national ambition to improve disaster risk governance, but institutional mandates remain overlapping and coordination mechanisms remain weak. Other key institutional actors include L'Agence Nationale de Gestion des Urgences et Catastrophes Humanitaires en abrégé (ANGUCH), Direction Générale de la Protection Civile (DGPC), Direction Nationale d l'Hydraulique (DNH), Agence Nationale de la Météorologie de Guinée (ANM), and Agence Nationale de Sécurité Sanitaire (ANSS).

Despite the formal designation of these institutions, Guinea faces critical gaps in interoperability, data sharing, and operational coordination. There is no integrated national system for monitoring and reporting loss and damage across hazard types and geographic zones. Post-disaster needs assessments (PDNAs) are conducted ad hoc and without standardised methodology. Economic and non-economic loss quantification remains largely absent. Local authorities and community actors are excluded from systematic data collection and recovery planning processes.

The process to develop the Plan National de Développement Économique et Social (PDNES 2026–2030) also presents an important opportunity to embed loss and damage assessment and response into Guinea’s development planning cycle, but this requires technical capacity that currently does not exist.

Guinea’s national assessments, including SNNRC 2024–2030 and institutional analyses from CENAGCUE, highlight an urgent need to strengthen multi-level disaster risk governance and build a comprehensive system for addressing loss and damage. National and subnational actors lack clarity in roles, coordination mechanisms, and standard operating procedures (SOPs). There are also major gaps in technical capacity, data integration, early warning, and post-crisis response protocols.

To address these findings, the government has established the following priorities:

- Establishing decentralized governance structures with clearly defined mandates and SOPs;

- Developing a national system for systematic loss and damage assessment, including slow-onset events and non-economic losses Institutionalizing PDNAs and linking them to planning and resource allocation processes;

- Enhancing knowledge generation, monitoring and evaluation systems, and early warning tools, particularly for high-risk populations; and

- Building the capacity of local authorities and national institutions, CENAGCUE and DGPC to operationalize risk management aligned with the Sendai Framework for Disaster Risk Reduction and Article 8 of the Paris Agreement.

Despite progress in policy and institutional development, Guinea faces persistent barriers that limit its capacity to avert, minimize, and address loss and damage. These include:

- weak decentralized implementation capacity, especially at regional and community levels;

- fragmented and under-resourced institutional architecture, with overlapping mandates and limited interagency coordination;

- lack of operational tools and protocols for real-time risk assessment, post-disaster data collection, and evidence-based recovery planning;

- absence of an integrated national system to monitor and report loss and damage across hazard types and geographic zones; and

- inadequate financing, human resources, and technology for sustained institutional strengthening.

Guinea currently lacks the institutional systems, technical methodologies, and financing frameworks to systematically assess, attribute, quantify, report, and finance responses to these losses and damages. The World Bank CERP addresses emergency response coordination; the PDNES addresses development planning. Neither addresses the systemic gap in Guinea’s capacity to identify, measure, govern, and finance responses to loss and damage as a distinct category of climate impact. This is the specific gap this technical assistance is designed to fill.

This technical assistance is designed to address these systemic gaps by supporting Guinea to establish a fit-for-purpose national loss and damage assessment framework, enhance vertical coordination, and strengthen institutional readiness to manage future climate shocks. It aligns with the Santiago Network’s mandate to provide tailored, country-driven support for developing countries most vulnerable to climate change impacts.

Further, this technical assistance is explicitly grounded in the distinction between loss and damage on the one hand, and adaptation and humanitarian response on the other, consistent with Article 8 of the Paris Agreement and the mandate of the Santiago Network.

## Objectives and expected impact of the technical assistance

The overall objective of this technical assistance is to enable the Republic of Guinea to establish a fit-for-purpose national system for assessing, governing, and financing responses to climate-induced loss and damage, thereby reducing Guinea’s structural vulnerability to the economic and social consequences of unavoidable climate impacts. Specific outcomes include:

- Establishing a national methodology and operational data system for quantifying economic and non-economic climate loss and damage across hazard types, geographic zones, and vulnerable population groups.

- Strengthening multi-level governance and institutional coordination for loss and damage response, from national to regional and local levels, with clear mandates, standard operating procedures, and interagency protocols.

- Building Guinea’s institutional readiness to access climate finance for loss and damage response, with a concrete pathway to a funding request to the Fund for responding to Loss and Damage (FRLD).

## Scope, activities and expected results of the technical assistance

The technical assistance is expected to deliver the following components:

- Identification and assessment of loss and damage needs and priorities

This component addresses the fundamental absence of a systematic national methodology for quantifying, attributing, and reporting economic and non-economic climate loss and damage in Guinea. Key expected results include:

Expected results:

- A comprehensive data gap and needs analysis covering all major hazard types (including sudden-onset and slow-onset), geographic zones, and vulnerable population groups, including women, youth, elderly, and persons with disabilities.

- A national methodological framework for quantifying economic loss and damage (including crop loss, infrastructure damage, income and productivity losses, asset destruction) and non-economic loss and damage (i.e. loss of life, displacement, cultural heritage loss, biodiversity and ecosystem loss, psychosocial impacts, traditional knowledge loss), aligned with IPCC definitions and WIM/Article 8 terminology.

- An interactive, web-based national loss and damage dashboard consolidating data from CENAGCUE, ANM, DNH, ANSS, ANGUCH, and DGPC, designed for interoperability, regular update, and public access at appropriate levels.

- Training and mentoring for regional technical groups in PDNA+ methodology, attribution analysis, and ex-post loss and damage assessment protocols, with relevant regional technical staff trained across Guinea’s four natural regions.

- Strengthen governance and institutional arrangements

This component addresses Guinea’s fragmented institutional architecture and weak coordination mechanisms for loss and damage response.

Expected results:

- Capacity and gap assessment of institutional arrangements, policy and planning instruments, and the enabling environment for loss and damage finance.

- Recommendations on institutional roles and responsibilities, with defined standard operating procedures for coordinated responses.

- Recommendations for strengthening existing structures and complementarity across government ministries and departments.

- Recommended approaches for effective consultation with local communities and vulnerable populations.

- Technical guidance to integrate loss and damage into local development plans and upcoming PDNES 2026-2030.

- Enable access to action and support, including finance, technology and capacity-building for implementation

This component builds Guinea’s institutional readiness to access climate finance specifically for loss and damage response, with a focus on the FRLD as the primary finance pathway.

Expected results:

- A comprehensive FRLD readiness assessment evaluating Guinea’s institutional capacity against FRLD eligibility and direct access requirements, including environmental and social safeguards, fiduciary standards, gender policy compliance, and monitoring, evaluation and learning systems.

- A gap-filling and capacity-building plan targeting the specific fiduciary, safeguards, and institutional weaknesses identified in the readiness assessment.

- A draft FRLD funding request grounded in the evidence, priorities, and institutional framework established under Components 1 and 2, targeting a project or programme addressing Guinea’s most urgent and quantified loss and damage response needs.

- A comprehensive financing framework mapping existing donor-funded initiatives, identifying financing gaps, and designing a coherent multi-source loss and damage financing architecture for Guinea aligned with PDNES 2026–2030 priorities.

## Geographical scope and target beneficiaries

The technical assistance will have a national scope, while prioritising institutional engagement and field-based consultations in climate-exposed regions and localities where loss and damage is already materialising. Priority attention will be given to areas affected by recurrent floods, droughts, landslides, coastal erosion, sea-level rise, food insecurity and degradation of productive ecosystems, including selected localities in Middle Guinea, Upper Guinea, Maritime Guinea and high-risk urban/peri-urban zones such as Conakry, which will be confirmed with government counterparts at the outset.

The primary institutional beneficiaries will include the national entities responsible for disaster risk management, climate change, hydrometeorological services, water resources, health surveillance, civil protection, local development planning and climate finance coordination, including CENAGCUE, ANGUCH, DGPC, ANM, DNH, ANSS and relevant sector ministries. The technical assistance will also support regional and local authorities, technical services, communal planning structures and community-based actors that are expected to apply the loss and damage assessment tools, protocols and coordination mechanisms.

Beyond their role as beneficiaries of the results, these agencies are expected to assume defined functions in the management and governance of the technical assistance itself. It is envisaged that implementation will be steered by an inter-ministerial steering committee, convened under the authority of the ministry responsible for environment and climate change, with CENAGCUE serving as technical secretariat, meeting quarterly to provide strategic direction, validate deliverables and resolve interagency issues. CENAGCUE and ANGUCH will co-lead day-to-day technical coordination through a standing interagency technical working group responsible for guiding the loss and damage assessment methodology, the national dashboard and the standard operating procedures. ANM, DNH and ANSS will act as designated data providers and system co-owners for hydrometeorological, water-resources and health-surveillance data respectively, with named focal points and data-sharing protocols agreed during the inception phase. DGPC will lead the integration of assessment and response protocols into civil protection operations at regional and prefectural levels, while the ministry responsible for planning will ensure alignment of outputs with the PDNES 2026–2030 process. Regional authorities and communal planning structures will co-convene field consultations and host the regional technical groups trained under Component 1. These management and governance arrangements, including decision-making, escalation and interagency engagement procedures, will be reviewed and formalised with the selected implementer at the outset of the technical assistance.

Indirect beneficiaries will also include climate-exposed communities whose lives, livelihoods, assets, ecosystems and social systems are increasingly affected by climate-related shocks and slow-onset processes. Particular attention will be given to women, youth, children, persons with disabilities, poor households, female-headed households, smallholder farmers, pastoralists, fisherfolk, informal urban residents and other vulnerable groups that are often underrepresented in conventional disaster risk management and recovery systems.

The technical assistance will ensure that local knowledge, gender-differentiated vulnerabilities and non-economic losses are systematically captured. Consultations will therefore assess not only damage to infrastructure, crops and productive assets, but also losses related to health, education, psychosocial well-being, social cohesion, cultural practices, access to water and land, displacement, food security and dignity. This will assist Guinea in moving from fragmented post-crisis reporting toward a more operational, inclusive and finance-ready national system for assessing and responding to climate-induced loss and damage.

## Complementarities with ongoing initiatives / activities

Guinea has undertaken a series of policy, institutional, and operational initiatives over the past decade to strengthen disaster risk governance and climate resilience. While these initiatives have established important structural foundations, none addresses the specific gap this technical assistance is designed to fill: the systematic assessment, quantification, governance, and financing of responses to climate-induced loss and damage in mangrove-rice socio-ecological territories already beyond the threshold of adaptation.

The Stratégie Nationale de Réduction des Risques de Catastrophes (SNRRC 2019–2023) provided Guinea's first structured DRR policy framework aligned with the Sendai Framework and supported the establishment of national and subnational coordination structures, including the Comité National de Gestion des Catastrophes and over 120 Groupes d'Action Local (GAL) led by ANGUCH. These structures focus on emergency preparedness and disaster response — not on the slow-onset, cumulative losses that constitute the defining climate damage pattern in coastal Maritime Guinea. The SNRRC's successor framework, the Plan Stratégique SNRRC 2024–2030 led by CENAGCUE, renews Guinea's commitment to improved disaster risk governance, early warning, and post-disaster response mechanisms, and explicitly references the need to integrate loss and damage data into national decision-making. This technical assistance directly operationalises that ambition by providing the methodological tools, institutional protocols, and financing pathway that the SNRRC 2024–2030 calls for but does not itself deliver.

At the operational level, the World Bank Contingent Emergency Response Project (CERP) addresses emergency response coordination through ANGUCH and ANIES, focusing on immediate relief, early response, and essential goods provision. The CERP's scope is deliberately bounded to acute emergency response and does not extend to the slow-onset processes — progressive salinisation, chronic coastal erosion, mangrove degradation, dike failure — that are the dominant loss and damage pathway in the target territories. This technical assistance is fully complementary to the CERP: it builds the upstream assessment frameworks and institutional methodologies that feed into post-event evaluation, and provides the downstream financing architecture that links loss quantification to recovery investment planning.

The French Development Agency (AFD)-financed Système d'Aménagement Rural et de gestion des ressources naturelles dans les Territoires côtiers et Estuariens du littoral guinéen (SARITEM) programme has invested in the hydraulic rehabilitation and mangrove-rice perimeter management of coastal Guinea, including technical and socio-economic diagnostics of degraded perimeters in Boffa, Boké, and Forécariah. The SARITEM-2 / RETESARIMA initiative — a climate loss and damage recovery initiative targeting the same coastal mangrove territories — provides the primary field evidence base, territorial framing, and institutional relationships within which this technical assistance is anchored. The Santiago Network TA is explicitly designed to strengthen the loss and damage governance and financing dimensions that the SARITEM framework has identified as critical institutional gaps, while avoiding any duplication of the hydraulic rehabilitation and perimeter management activities that AFD programmes in the region address.

The PDNES 2026–2030 presents a pivotal integration opportunity: the institutional frameworks, SOPs, and L&D assessment methodologies produced under this technical assistance will be formally submitted for integration into PDNES planning instruments, ensuring that coastal territorial loss and damage is mainstreamed into Guinea's development investment cycle beyond the technical assistance period. To secure this integration pathway, the ministry in charge of planning, as the institution leading the preparation of the PDNES 2026–2030, will be directly engaged in the implementation of the technical assistance, including through membership of the steering committee, and the Office of the President will be kept informed through existing high-level coordination channels to ensure political ownership of the resulting frameworks.

Complementary technical partnerships with UNDP, FAO, UNICEF, and the WACA programme (World Bank West Africa Coastal Areas Management Programme) have generated relevant data, community resilience investments, and institutional relationships in the target territories. These initiatives have, however, remained fragmented and insufficiently institutionalised at the subnational level, and none has established a dedicated framework for the assessment and financing of non-economic losses — including women's land tenure, cultural heritage, traditional ecological knowledge, and psychosocial impacts — in the mangrove-rice systems of coastal Guinea. This technical assistance fills precisely that gap, building on rather than duplicating existing investments.

## Estimated financial need for delivery of the technical assistance

### Total amount of financial support available for the delivery of the technical assistance

The following table indicates the total maximum amount of financial support available for the delivery of technical assistance under this Call for Proposals. Applicants are encouraged to consider the cost-effectiveness and delivery efficiency in their financial proposals. The maximum amount indicated below must not be exceeded. As per the guidelines and procedures for responding to requests for technical assistance, applicants are invited to indicate if they are able to cover the full cost of the technical assistance or provide co-financing or in-kind contributions.

| Currency | Amount | Amount in words |
| --- | --- | --- |
| USD | 650,000 | Six hundred and fifty thousand |

As per the guidelines and procedures for responding to requests for technical assistance, applicants are invited to indicate if they are able to cover the full cost of the technical assistance or provide co-financing or in-kind contributions.

As per the UNOPS policy, Implementing Partners which are not part of the UN system, are required to conduct an independent audit at the end of implementation for all grants with a value of over USD 250,000. Consequently, respective applicants must include a dedicated budget line for project audits within their financial proposals to ensure compliance.

## Timeline for technical assistance delivery

The expected duration of the delivery of the technical assistance is:

| MONTH(S) | 18 |
| --- | --- |

The proposal should seek to take advantage of any interlinkages between the components outlined in section 2.4, and similar processes ongoing in the country to achieve delivery efficiency.

## Applicant eligibility

### Applicant category(ies)

Members of the Santiago Network are eligible to respond to this Call for Proposals. Interested OBNEs not yet Members of the Santiago Network may respond to this Call for Proposals and at the same time submit their Expression of Interest for membership in line with the membership guidelines. In such cases, the Expression of Interest must be submitted prior to the deadline for proposal submissions indicated in this Call for Proposals.

### Applicant country of registration and nationality

Applicants that are included or excluded under this Call for Proposals with regard to country of registration and nationality (for individuals) are as follows:

Open to all countries The applicant must demonstrate at least 10 years of experience in implementing projects and initiatives related to averting, minimising and/or addressing loss and damage in Africa, particularly francophone West Africa. The applicant, or consortium, should ensure the effective and efficient delivery of the component(s) of the technical assistance in this Call for Proposals, noting, where applicable, the different levels of local, national, regional and international as well as subject matter expertise and experience required.

### Additional conditions of eligibility

The applicant shall not fall under any of the conditions listed in the Instructions to Applicants, Article 1, which makes the applicant ineligible for the financial support under this Call for Proposals.

At the time of application, the applicant (and consortium members, where applicable) must either be a Member of the Santiago Network, or have submitted an Expression of Interest for membership prior to the deadline for proposal submissions indicated in this Call for Proposals (please see the Santiago Network membership page for more information related to the membership process). Only proposals of OBNEs already Members of the Santiago Network or OBNEs who have submitted their Expression of Interest prior to the deadline and are subsequently admitted as Members in line with the membership guidelines, will be considered (see also preliminary screening criteria outlined in section 4 below). It is highly recommended that interested OBNEs not yet Members of the Santiago Network, submit their Expression of Interest as soon as possible to avoid any delays.

The applicant must comply with the Santiago Network Guidelines on preventing potential and addressing actual and perceived conflicts of interest in relation to the Santiago Network and disclose any potential or actual conflict of interest. Applicants are further required to disclose, where applicable, if and how they have been involved in the preparation of the request for technical assistance subject of this Call for Proposals.

The applicant’s suitability to deliver the technical assistance set out in this Call for Proposals, will be determined in line with the Guidelines and procedures for responding to requests for technical assistance. In addition, the Santiago Network Secretariat will carry out a capacity, Protection from Sexual Exploitation and Abuse (PSEA) and due diligence assessment of the selected applicant.

## Content of proposal submissions

Applicants shall submit the following:

- Proposal (Note: Information exceeding the word limit indicated in the template will not be considered)

- Financial proposal / Budget (To be submitted through the Grant+ platform via the budget template)

- Annex 1: Declarations (Note: In case of a consortium, each consortium partner is required to complete and sign the declarations individually. All signed forms shall be attached to the proposal when submitting.)

- Annex 2: Risk/issues register (Note: Include any potential risks/issues anticipated in implementation of the set objectives)

- Annex 3: any relevant supplementary documentation, including project summaries, reports, research papers, reference letters, etc.

Applicants must carefully read and understand the following documents before completing the Proposal and Annexes:

- Requirements in this Call for Proposals

- Instructions to Applicants

- Guidelines and procedures for responding to requests for technical assistance

- Guidelines for managing funding provided for technical assistance

- Guidelines on preventing potential and addressing actual and perceived conflicts of interest in relation to the Santiago network

## Partial proposals

Partial proposals will not be accepted. Applicants shall submit a proposal for the full scope of the technical assistance and address all of the requirements in this Call for Proposals. Evaluation will be based on compliance with all requirements.

## Sub-granting and contracting

Sub-granting and contracting are only permitted under this Call for Proposals as follows:

| Sub-granting | Permissible |
| --- | --- |
| Contracting | Permissible |

In keeping with the relevant guidelines and procedures of the Santiago Network relating to membership and technical assistance, only Members of the Santiago Network will be eligible to conduct technical activities that are material to the request.

## Proposal currency

The proposal budget shall be prepared in the following currency(ies): United States Dollars (USD)

## Language of proposals

All proposals, information, documents and correspondence exchanged between the Santiago Network Secretariat / UNOPS (as co-host of the Santiago Network Secretariat) and the applicant shall be in: English

## Proposal submission

The deadline for the submission of proposals is XXX XX, 2026. Proposals shall be submitted using the following method: UNOPS Grant+.

Applicants must:

- Create their profile in Grant+: grantplus.unops.org

- Create their organization profile, and

- Apply to the funding opportunity [UNOPS/FO/2026/29] Call for Proposal: SANTIAGO NETWORK CFP/SN/24039/2026/GUI/028 - Strengthening Guinea’s national system for assessing, governing and financing responses to climate-induced loss and damage.

The application consists of:

- Entering basic information about the proposal

- Creating the proposal budget in the platform

- Uploading the narrative proposal and other required documents, see section 2.11 above

mult

Note: Grant+ is the new UNOPS grant management platform. An online information session showing how to upload proposals will take place on XX XXX 2026 at XX:00 AM ( GMT+1) / XX:00 AM (GMT+2). The meeting will be held via Zoom. Register in advance via this link: XXX

User guides and how-to videos are also available on the platform by clicking on the “?” or “Guidance” at the top right of the page.

Despite numerous tests, it is possible that the first users will encounter bugs. In this case they can contact UNOPS System Support by clicking on the “?” at the top right of the grantplus.unops.org pages, once registered in the platform.

Refer to Article 10, “Proposal Submission”, of the Instructions to Applicants for details on the specific requirements for proposal submission.

## Type of legal instrument

The applicable legal instrument(s) are identified hereunder. A template is provided with this Call for Proposals for reference. The agreement will be entered into directly with UNOPS.

- Grant Support Agreement

- UN2UN Agreement

## Contact information and requests for clarification

All correspondence, notifications and requests for clarifications in relation to this Call for Proposals shall be sent to:

| Name | Santiago Network Secretariat |
| --- | --- |
| Title | N/A |
| Email | proposals@santiago-network.org |

Requests for clarifications on this call for proposals may be made no later than XXX XX, 2026 by sending an email to the contact information above.

## Important dates and deadlines

The following tables provide the key dates and deadlines about this Call for Proposals.

|  | Date | Time | Timezone |
| --- | --- | --- | --- |
| ### Request for clarification | XXX XX, 2026 | [23:59] | [GMT] |
| ### Submission of proposals | XXX XX, 2026 | [23:59] | [GMT] |
| ### Expected agreement start date | XX XXX, 2026 |  |  |

# REQUIREMENTS

## Approach and methodology

In their proposal, the applicant has to outline the approaches and principles they will follow throughout the delivery of the technical assistance, covering the following areas:

##### Health and Safety Requirements, with a particular focus on the context within which the technical assistance will be provided

##### Social and Environmental Requirements (such as gender and social inclusion, environmental protection, climate and resource efficiency considerations, and application of the do-no-harm principle)

##### Protection from Sexual Exploitation and Abuse Requirements

##### Sustainability Requirements and retention of capacity in the country.

## Implementation Plan requirements

Using the activities and expected results detailed in section 2.4, and in view of achieving the outcomes and objectives set out in the request for technical assistance, complete the Implementation Plan. The Implementation Plan should accurately show the sequence and timeframe for the delivery of each activity and output and take into account the parameters related to the expected timeline and budget limits detailed above.

## Monitoring, Evaluation and Learning Plan requirements

Complete the Monitoring, Evaluation and Learning (MEL) Plan (section 5 in the Proposal template). Applicants are encouraged to collect, analyze and report on disaggregated data by sex, age and disability (for relevant indicators), capture lessons learned and make provisions for retention of capacities in the country.

Members receiving financial support directly from the Santiago Network Secretariat, will report in accordance with the provisions stipulated in the contractual arrangement as well as where appropriate noting how they contributed to the overall goals and functions of the Santiago Network.

## Budget requirements

- Applicants are invited to provide and include best estimates to implement the set objectives as described under the scope of this Call for Proposal (CFP) in sections 2.4 and 2.5, giving due consideration to the cost-effectiveness and delivery efficiency of the activities to be undertaken (see also financial criteria in section 4.3). The indicated budget ceiling must not be exceeded.

- At a minimum, the budget must include:

  - An estimate of direct costs, which include all of the expenses that are required for, and can be tracked directly to, the financial support provided for the delivery of technical assistance. Direct costs must be broken down by thematic area, expense subcategory, by expense line item and by year.

  - A description of assumptions or justifications underlying the estimates.

  - A breakdown of costs by component indicated under Section 2.4.

- The costs will be eligible only if these are incurred for the purpose of delivering this technical assistance and within the duration mentioned in the legal instrument (including any amendments) entered into with UNOPS.

- Article II, Section 7, of the Convention on the Privileges and Immunities of the United Nations provides, inter alia, that the United Nations, including UNOPS as a subsidiary organ, is exempt from all direct taxes, except charges for public utility services, and is exempt from customs restrictions, duties, and charges of a similar nature in respect of articles imported or exported for its official use. All proposals shall be submitted net of any direct taxes and any other taxes and duties.

- Budgets must detail the level of indirect costs. In case of subgrants, indirect costs on the subgrant amount should be calculated and presented separately.

- Applicants will be invited to specify if they have existing resources that could be used towards funding the technical assistance activities (full financing, co-financing or in-kind contributions).

# EVALUATION METHOD AND CRITERIA

Proposals submitted in response to this Call for Proposals shall be evaluated following the cumulative analysis methodology, which consists of the following steps:

- Preliminary screening: This includes an assessment of whether proposals comply with the formal and eligibility criteria stated in Table 1: Formal and eligibility criteria. All proposals which pass this stage will go through a subsequent evaluation as follows.

- Technical evaluation: This assesses the technical points achieved by each proposal, as per the maximum obtainable points assigned per criteria group in Table 2.1: Parts of the technical proposal evaluation. Only proposals that meet the minimum threshold indicated in Table 2: Technical criteria shall be considered substantially compliant at this stage. Evaluation of the technical proposals shall be completed prior to opening the financial proposals.

- Financial evaluation: Financial proposals will only be opened for proposals that have achieved the minimum threshold in the technical evaluation. Financial proposals shall be checked for any mathematical errors in accordance with Article 15, “Minor Informalities, Errors or Omissions” in the Instructions to Applicants. The total financial proposal points achieved for each proposal are determined in accordance with Table 3: Financial criteria.

- Combined analysis: This evaluation will be conducted based on a combined analysis, analyzing all of the relevant costs, risks and benefits for each proposal. The combined analysis includes the scores from both the technical evaluation, including factors such as risks, sustainability, and others, and the financial evaluation, using a predefined weighting method.

The maximum number of points that an applicant may obtain for its proposal are as follows:

- Technical proposal: 80 points

- Financial proposal: 20 points

The maximum total number of points an applicant may obtain for both the technical and financial proposals is 100. The weighting of the technical and financial proposals will be 80:20. The technical and financial proposals must be aligned, ensuring that budgetary allocations correspond to the activities and deliverables described in the technical proposal.

The Santiago Network Secretariat may request clarification or further information in writing from applicants at any point during the evaluation process. In this case, any response from an applicant shall not modify the substance of the proposal, including both the technical and financial aspects of the proposal. The Santiago Network Secretariat may use such information to interpret and evaluate the relevant proposal.

The evaluation of a proposal by the Santiago Network Secretariat shall be carried out against the evaluation criteria described in the following tables.

## Preliminary screening

| ## Table 1 FORMAL AND ELIGIBILITY CRITERIA |  |
| --- | --- |
| Criteria evaluated on a pass/fail basis during the preliminary screening | Documents to establish compliance with the criteria |
| - The applicant is a Member of the Santiago Network or has submitted an Expression of Interest in line with the membership guidelines prior to the deadline indicated for proposal submissions in this Call for Proposals and subsequently approved as Member. | - Declarations - Santiago Network membership database / Expression of Interest for Santiago Network membership |
| - The applicant is eligible as defined in Article 1, “Applicant Eligibility” in the Instructions to Applicants and the Guidelines on preventing potential and addressing actual and perceived conflicts of interest in relation to the Santiago Network. | - Proposal - Annex 1: Declarations |
| - The proposal is complete and includes all completed forms and other documentation requested in the Particulars, ‘Content of proposal submissions’. | - All documentation requested in the Particulars, ‘Content of proposal submissions’ |
| - The applicant accepts the conditions in the template for agreement, as specified in the Particulars, ‘Type of legal instrument’. | - Annex 1: Declarations |
| - The applicant must demonstrate experience in implementing projects and initiatives on topics related to climate risk assessment, post-disaster planning, non-economic loss and damage, and climate finance readiness in Africa, particularly in francophone West Africa, or similar contexts. | - Proposal - Annex 3: Supporting documents, including project summaries, reports, research papers, reference letters, etc. |
| - The applicant must demonstrate a minimum of 10 years of proven experience implementing similar types of technical assistance/activities as outlined in this Call for Proposals. | - Proposal - Annex 3: Supporting documents, including project summaries, reports, research papers, reference letters, etc. |

## Technical evaluation

| ## Table 2 TECHNICAL CRITERIA |  |
| --- | --- |
| Criteria evaluated based on scoring during the technical evaluation | Documents to establish compliance with the criteria |
| The maximum number of technical points obtainable is detailed in Table 2.1: Parts of the technical proposal evaluation. To be technically compliant, applicants must obtain a minimum threshold of 70% of the total obtainable points. | - Proposal - Annex 3: Supporting documents, including project summaries, reports, research papers, reference letters, etc. |

|  | ## Table 2.1 Parts of the technical proposal evaluation | Obtainable points |
| --- | --- | --- |
| 1. | Applicant’s capacity and expertise (see Table 2.1.1) | 20 |
| 2. | Proposed methodology, approach and implementation plan (see Table 2.1.2) | 30 |
| 3. | Key personnel proposed (across the consortium, if applicable) (see Table 2.1.3) | 15 |
| 4. | Relevant past experience | 15 |
| Total technical proposal points |  | 80 |

|  | ## Table 2.1.1 Part 1: Applicant’s capacity and expertise |  |
| --- | --- | --- |
| No. | Criteria to be evaluated | Documents to establish compliance with the criteria (not exhaustive) |
| 1.1 | The applicant has the general organizational capability to support effective implementation: management structure; financial stability and project financing capacity; management controls; and the extent to which any work would be sub-granted/contracted. | Copy of audited financial statements for the last 3 years of the lead applicant - Proposal |
| 1.2 | The applicant has demonstrated their technical expertise and experience to effectively deliver the technical assistance activities. | - Proposal |
| 1.3 | The applicant has knowledge and experience required for supporting developing countries in climate risk assessment, post-disaster planning, non-economic loss and damage, and climate finance readiness. | - Proposal |
| 1.4 | The applicant has a presence in the relevant region, country or area. | - Proposal |
| 1.5 | The applicant has the capacity, knowledge and experience to engage with national and local stakeholders, including the application of co-design approaches, and undertake capacity building workshops in an inclusive manner and with a diverse range of actors. | - Proposal |
| Total points for Part 1 – 20 |  |  |

|  | ## Table 2.1.2 Part 2: Proposed methodology, approach and implementation plan |  |
| --- | --- | --- |
| No. | Criteria to be evaluated | Documents to establish compliance with the criteria (not exhaustive) |
| 2.1 | The proposal is substantially compliant and does not contain any material deviation(s) from the minimum requirements as stipulated in this Call for Proposals document, which indicates the applicant’s understanding of these requirements. | - Proposal |
| 2.2 | The applicant’s proposed approach and methodology is consistent with the objectives and targeted outcomes of the technical assistance detailed in this Call for Proposals, accounts for the different skillsets required, and provides sufficient details on how the results are intended to be delivered. | - Proposal |
| 2.3 | The proposed approach emphasizes an implementation strategy that benefits from a diversity of expertise and engagement with government actors, including where applicable at the local level. | - Proposal |
| 2.4 | The proposal provides a strategy for engaging relevant actors and stakeholders to ensure consideration of the needs of vulnerable people, Indigenous Peoples, women, youth and children, and the local population most affected by climate-induced loss and damage. | - Proposal |
| 2.5 | The Implementation Plan demonstrates the applicant's capacity to plan and implement the technical assistance activities within the identified timeliness, ensuring delivery effectiveness and efficiency, and accounting for internal/ external risks, proposing appropriate mitigation actions. | - Proposal |
| 2.6 | The proposal satisfactorily describes how the Health and Safety, and Social and Environmental (HSSE) requirements, in relation to the technical assistance activities will be met. | - Proposal |
| 2.7 | The proposal satisfactorily describes how the Protection from Sexual Exploitation and Abuse (PSEA) requirements in relation to the technical assistance activities will be met. | - Proposal |
| 2.8 | The applicant’s proposed sub-grantees, if identified, that will undertake relevant technical assistance activities, have demonstrated the capacity to undertake the work and are appropriately located to undertake these activities. (If the applicant does not require sub-grantees, the proposal will be assigned the maximum points for this criterion). | - Proposal |
| 2.9 | The Monitoring, Evaluation and Learning Plan details how different elements of the technical assistance will be monitored, controlled, and provides verifiable indicators and a strategy for capturing knowledge, lessons learned and good practices. | - Proposal |
| 2.10 | ##### The proposal provides a strategy for the long-term sustainability of activities and retention of capacity in the country. | - Proposal |
| Total points for Part 2 – 30 |  |  |

|  | ## Table 2.1.3 Part 3: Key personnel proposed |  |
| --- | --- | --- |
| No. | Criteria to be evaluated | Documents to establish compliance with the criteria (not exhaustive) |
| 3.1 | The composition and structure of the applicant’s proposed team is appropriate and the proposed management roles and other key personnel roles are suitable for the implementation of the technical assistance activities, including elaboration on regional, national and local expertise, as appropriate for the activities. | - Proposal, Section 6 |
| 3.2 | The applicant describes and justifies its plan for the size and composition of its team, and where applicable the consortium partners and sub-grantees. | - Proposal, Section 6 |
| 3.3 | The qualifications and experience of the proposed key personnel meet the established requirements, including, but not limited to expertise in: ##### coordination - regional / country / local - climate change / loss and damage financing and proposal writing ##### stakeholder engagement / facilitation - institutional strengthening | - Proposal, Sections 8 and 9 |
| Total points for Part 3 – 15 |  |  |

## Financial evaluation

| ## Table 3 FINANCIAL CRITERIA |  |  |
| --- | --- | --- |
| Criteria evaluated based on a cumulative analysis methodology during the financial evaluation |  | Documents to establish compliance with the criteria |
| 1. | The cost-effectiveness and delivery efficiency of the activities to be undertaken. | - Financial proposal |
| 2. | Applicants comply with the maximum budgets stipulated in the Budget requirements. | - Financial proposal |
| 3. | The applicant has provided sufficient justification of budget lines and lump sums, and given appropriate consideration to delivery and financial efficiency. | - Financial proposal |
| 4. | The allocation of budget among different categories is appropriate, particularly the allocation between activities and the operational budget. | - Financial proposal |
| 5. | The applicant’s cost estimates and the assumptions made for such estimates are reasonable. | - Financial proposal |
| Total financial proposal points - 20 |  |  |

Santiago Network COP28 decision: https://unfccc.int/documents/636316; CMA5 decision: https://unfccc.int/documents/636315

Decision 12/CMA.4, endorsed in decision 11/CP.27, Annex I

The Instructions to Applicants are a standard UNOPS document. For the purpose of this Call for Proposals 'Grants/Funding' references refer to ‘the provision of technical assistance’, ‘Joint Venture, Consortium or Association’ references refer to ‘networks or consortium’.

Sub-grant is when an entity is selected by the implementing partner to implement activities on behalf of the implementing partner and complies with the same principles as outlined in the UNOPS Operational Instruction on Grant Support.

Contracting is done when an implementing partner procures services, goods or works using the procurement procedures of the IP.

These are standard UNOPS templates to showcase the structure and general terms & conditions to be expected.

In case a UN partner is selected to carry out all or part of the activities