Guinea GCF Readiness — GCF-compliant Logical Framework (aligned to the Revised RRMF & the revised budget)

Direct Access · NDA: Ministry of Environment and Sustainable Development · Delivery Partner: ANAFIC · Total request USD 2,620,590 · 36 months · NDA-validated for submission

| Objective (budget) | Outcome & outcome indicator (0–3 scaler) | Output | Output indicator | Unit | Base | Target | Disaggregation | Means of verification (Deliverable) | Budget (USD) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective 1: Capacity-building for climate-finance coordination & enabling environment — USD 660,000 (30%) |  |  |  |  |  |  |  |  |  |
|  | Outcome 1.1 — enhanced NDA/FP capacity incl. coordination. OI 1.1.1 (scaler): baseline 1 → target 3 | Output 1.1.1 — NDA/FP & stakeholders enhanced capacity | OI 1.1.1.1 Proportion of NDA/FP, Coordination Mechanism & stakeholders reporting enhanced capacity (X/total) | Percentage; denominator 120 participants | 0% | ≥70% of 120 | Sex; stakeholder group; NDC/NAP/LTS workstream | D1 — status report and pre/post capacity assessments | 150,000 |
|  | OI 1.1.2 (scaler) Coordination Mechanism effectiveness: baseline 0 → target 3 | Output 1.1.2 — inclusive Coordination Mechanism | OI 1.1.2.1 Coordination Mechanism / Country Platform established or strengthened | No. of mechanisms/platforms | 0 | 1 | Type: Country Platform; Status: Establish | D2 — Status report on country coordination mechanism / platform | 120,000 |
|  |  |  | OI 1.1.2.2 Number of coordination meetings/dialogues undertaken (+ participants F/M in APR) | No. of meetings/dialogues | 0 | 9 meetings/dialogues | Total meetings/dialogues; participants (F/M) | D2 (as above) | (in D2) |
|  | Outcome 1.2 — strategic frameworks & policy instruments. OI 1.2.1 (scaler): baseline 1 → target 3 | Output 1.2.1 — frameworks & instruments created/updated/strengthened | OI 1.2.1.1 Number of inclusive NDCs, NAPs & LTSs developed or advanced | No. of frameworks | 0 | 3 | Strategic framework: NDC/NAP/LTS; status developed/updated | D3, D4, D5 — NAP, NDC, LTS status reports | 30k / 45k / 25k |
|  |  |  | OI 1.2.1.2/1.2.1.3 Number of policy instruments / private-sector incentive mechanisms | No. of instruments | 0 | ≥1 | Policy-related; climate-investment-programming-related | D6 — private-sector engagement policies/regulations | 90,000 |
|  | Outcome 1.3 — DAEs met/maintained accreditation. OI 1.3.1: baseline 0 → target 2 | Output 1.3.1 — institutional gaps of DAEs addressed | OI 1.3.1.1 Number of applicants/DAEs with capacity, systems, policies & tools compliant with GCF accreditation | No. of entities | 0 | 2 (ANAFIC and Access Bank Guinea; subject to GCF Accreditation Team confirmation) | Pre-accreditation; post-accreditation support | D7 — Status report on accreditation capacity building | 200,000 |
| Objective 2: Paradigm-shifting GCF pipeline development & implementation (USP-2) — USD 1,320,000 (60%) |  |  |  |  |  |  |  |  |  |
|  | Outcome 2.1 — country programmes guide GCF investment. OI 2.1.1: N/A (D8 removed) | Output 2.1.1 — Country Programme (D8) | OI 2.1.1.1 Inclusive Country Programme — NOT APPLICABLE | — | N/A | N/A | D8 removed per GCF comment 2.1.1; absorbed into Outputs 1.1.2 & 1.2.1 | D8 — Country Programme (removed) | 0 |
|  | Outcome 2.2 — high-quality CNs/FPs. Baseline 0 → target 3 submission-ready FPs; GCF screening status reported separately | Output 2.2.1 — enhanced CN/FP-development capacity | OI 2.2.1.1 Primary: studies, assessments and actions supporting investment-grade CNs/FPs; supplemental: project-preparation participants reporting enhanced capacity | No. studies/actions; participants; percentage | 0 | ≥5 studies/assessments; 60 participants; ≥70% reporting enhanced capacity | Study type; sex; stakeholder group | D9-D10 supporting studies and capacity records | (in D9/D10) |
|  |  | Output 2.2.2 — investment-grade CNs and submission-ready FPs aligned with national priorities | OI 2.2.2.1 Number of CNs prepared and NDA-validated; number of submission-ready FPs prepared and NDA-validated | No. of CNs / FPs | 0 | 5 CNs; 3 FPs | Product type; NDA-validation status; GCF screening status reported separately | D9 — Concept Notes; D10 — Funding Proposals | 228k / 700k |
|  | Outcome 2.3 — enhanced oversight processes/systems. OI 2.3.1 (scaler): baseline 1 → target 3 | Output 2.3.1 — enhanced NDA/DAE systems | OI 2.3.1.1 Primary: institutions reporting enhanced processes/systems; supplemental: systems/process packages established or strengthened | No. institutions; no. systems/process packages | 0 | 3 institutions; 3 systems/process packages | Institution type; system/process type | D11 — Status report on NDA/DAE oversight capacity | 392,000 |
| Objective 3: Knowledge-sharing & learning for national & regional cooperation — USD 220,000 (10%) |  |  |  |  |  |  |  |  |  |
|  | Outcome 3.1 — use of knowledge products. OI 3.1.1 (scaler): baseline 1 → target 3 | Output 3.1.1 — knowledge products generated & disseminated | OI 3.1.1.1 Number of inclusive knowledge products & resources | No. of products | 0 | ≥5 | Strategic framework: NDC/NAP/LTS-related | D12 — Knowledge Products / Compendium | 110,000 |
|  |  |  | OI 3.1.1.2 Number of inclusive knowledge-sharing events & platforms | No. of events/platforms | 0 | ≥4 + 1 | Event type; platform | D13 — Knowledge-sharing events & platform | 65,000 |
|  | Outcome 3.2 — regional/South-South cooperation. OI 3.2.1: baseline 0 → target 2 | Output 3.2.1 — regional/South-South partnerships established | OI 3.2.1.1 Number of regional/South-South partnerships, programmes, policies, MOUs, mechanisms established | No. of partnerships | 0 | 2 (Morocco, Senegal) | Status: Establish/Strengthen; partnerships/programmes/policies | D14 — Status report on regional/South-South partnerships | 45,000 |

Support costs: Independent evaluation USD 60,000 · PMC USD 168,000 (7.43%, ≤7.5%) · Contingency USD 67,800 (3%) · Delivery-partner fee USD 124,790 (5%) · TOTAL USD 2,620,590.

Notes: Aligned to the Revised RRMF core indicators. Outcome indicators use the applicable scaler; output indicators use validated absolute or percentage targets. Canonical targets are reconciled with the proposal, GPP mapping and budget. GCF screening or approval is reported only when formally confirmed. D8 remains removed and unbudgeted per GCF comment 2.1.1.